## Sheet1
Task ID | Task Name | Duration | Start | Finish | Status | Predecessors | Resources | Deliverable
1 | NISM - Implmenetation of the NISM team project | 77 Days | 2022-03-08 | 2022-05-23
2 | Stage 1 - Design Document Assignment | 43 Days | 2022-03-08 | 2022-04-18
3 | Team Formation | 3 Days | 2022-03-08 | 2022-03-11 | Completed
4 | Team Contract | 3 Days | 2022-03-11 | 2022-03-13 |  |  |  | Team Contract
5 | Assigned site study | 4 Days | 2022-03-14 | 2022-03-17
6 | Preparation of the draft bulleted list of appropriate governing bodies and regulations governing bodies and regulations | 5 Days | 2022-03-18 | 2022-03-22 |  | 5 |  | Draft bulleted list of appropriate governing bodies and regulations
7 | Bulleted list of appropriate governing bodies and regulations fine-tune & finialize | 2 Days | 2022-03-23 | 2022-03-24 |  | 6 |  | Bulleted list of appropriate governing bodies and regulations
8 | Shortlist of the intended audience, potential information that may be held, the industry (which may affect the sensitivity of the data), and the functionality | 4 Days | 2022-03-25 | 2022-03-28 |  | 7
9 | Preparation of the draft bulleted list of potential vulnerabilities based on the regulations | 5 Days | 2022-03-29 | 2022-04-01 |  | 8 |  | Draft bulleted list of potential vulnerabilities based on the regulations
10 | List of possible security vulnerabilities fine-tune & finialize | 2 Days | 2022-04-02 | 2022-04-03 |  | 9 |  | List of possible security vulnerabilities
11 | Preparation of the draft of tabular summary of recommendations & mitigations | 5 Days | 2022-04-04 | 2022-04-08 |  | 10 |  | Draft of tabular summary of recommendations & mitigations
12 | Tabular summary of recommendations & mitigations fine-tune & finialize | 2 Days | 2022-04-09 | 2022-04-10 |  | 11 |  | Tabular summary of recommendations & mitigations
13 | Preparation of the Design Document Report | 5 Days | 2022-04-11 | 2022-04-15 |  | 12 |  | Draft of the Design Document Report
14 | Design Document Report fine-tune & finialize | 3 Days | 2022-04-16 | 2022-04-18 |  | 13 |  | Design Document Report
15 | Stage 2 - Executive Summary Assignment | 34 Days | 2022-04-19 | 2022-05-23
16 | Preparation of tabulated summary of the work carried out with tools used, justification for tool selection, tests carried out and results | 5 Days | 2022-04-19 | 2022-04-23 |  | 14 |  | Draft of tabulated summary of the work carried out with tools used, justification for tool selection, tests carried out and results
17 | Tabulated summary of the work carried out with tools used, justification for tool selection, tests carried out and results fine-tune & finialize | 2 Days | 2022-04-24 | 2022-04-25 |  | 16 |  | Tabulated summary of the work carried out with tools used, justification for tool selection, tests carried out and results
18 | Preparation of analysis of results, supported by charts and graphs | 5 Days | 2022-04-26 | 2022-04-30 |  | 17 |  | Draft of analysis of results, supported by charts and graphs
19 | Analysis of results, supported by charts and graphs fine-tune & finialize | 2 Days | 2022-05-01 | 2022-05-02 |  | 18 |  | Analysis of results, supported by charts and graphs
20 | Preparation of discussion of key vulnerabilities, comparison with the initial report, explanation of differences and omissions | 5 Days | 2022-05-03 | 2022-05-07 |  | 19 |  | Draft of discussion of key vulnerabilities, comparison with the initial report, explanation of differences and omissions
21 | Discussion of key vulnerabilities, comparison with the initial report, explanation of differences and omissions fine-tune & finialize | 2 Days | 2022-05-08 | 2022-05-09 |  | 20 |  | Discussion of key vulnerabilities, comparison with the initial report, explanation of differences and omissions
22 | Preparation of draft of conclusions and recommendations for improvements/ mitigations ordered by business priority | 5 Days | 2022-05-10 | 2022-05-14 |  | 21 |  | Draft of conclusions and recommendations for improvements/ mitigations ordered by business priority
23 | Conclusions and recommendations for improvements/ mitigations ordered by business priority fine-tune & finialize | 2 Days | 2022-05-15 | 2022-05-16 |  | 22 |  | Conclusions and recommendations for improvements/ mitigations ordered by business priority
24 | Preparation of the Executive Summary Report | 4 Days | 2022-05-17 | 2022-05-20 |  | 23 |  | Draft of the Executive Summary Report
25 | Executive Summary Report fine-tune & finialize | 2 Days | 2022-05-21 | 2022-05-23 |  | 24 |  | Executive Summary Report